## Worksheet
Audit Preparation Planner
Task ID | Task Description | Responsible Party | Due Date | Status
Audit Scope Definition
AS-01 | Define audit objectives and scope with management | Lead Auditor, CFO | 2023-10-15 | Pending
AS-02 | Identify key business processes and controls to be reviewed | Audit Team, Department Heads | 2023-10-18 | In Progress
Resource Allocation & Scheduling
RA-01 | Assign audit team roles and responsibilities | HR, Audit Manager | 2023-10-16 | Pending
RA-02 | Develop audit schedule with key milestones and deliverables | Audit Manager, Project Coordinator | 2023-10-19 | Pending
Task ID | Task Description | Responsible Party | Due Date | Status
Document Gathering & Review
DC-01 | Collect financial statements and supporting documentation (Q3 2023) | Finance Team, Internal Auditor | 2023-10-25 | Pending
DC-02 | Review key policies and procedures related to internal controls | Audit Team, Compliance Officer | 2023-10-28 | In Progress
Evidence Collection & Testing Plan
ET-01 | Prepare testing protocols for high-risk processes (e.g., revenue recognition) | Audit Team Lead, Senior Auditor | 2023-10-30 | Pending
ET-02 | Conduct preliminary walkthroughs of key systems and processes | Audit Team, IT Security Officer | 2023-11-03 | Pending
Task ID | Task Description | Responsible Party | Due Date | Status
Process Testing & Control Evaluation
FT-01 | Test revenue cycle controls and transaction samples | Audit Team, Financial Analysts | 2023-11-06 | In Progress
FT-02 | Evaluate procurement and payment approval processes for compliance | Audit Team, Procurement Lead | 2023-11-08 | Pending
Data Analysis & Risk Assessment
DA-01 | Perform data analytics on financial transactions and anomalies | Data Analyst, IT Auditor | 2023-11-10 | Pending
DA-02 | Update risk assessment matrix based on fieldwork findings | Audit Manager, Risk Officer | 2023-11-13 | Pending
Task ID | Task Description | Responsible Party | Due Date | Status
Drafting Audit Findings & Recommendations
RF-01 | Compile initial audit findings and draft report sections | Audit Team, Documentation Specialist | 2023-11-16 | In Progress
RF-02 | Develop action plans and recommendations for control deficiencies | Audit Manager, Process Improvement Lead | 2023-11-18 | Pending
Management Review & Feedback Collection
MR-01 | Present draft findings to department heads for comment and validation | Audit Manager, Department Managers | 2023-11-20 | Pending
MR-02 | Document management responses and proposed corrective actions | Audit Team, Project Coordinator | 2023-11-25 | Pending
Task ID | Task Description | Responsible Party | Due Date | Status
Final Report Preparation & Distribution
FR-01 | Finalize audit report with management feedback incorporated | Audit Manager, Lead Auditor | 2023-11-30 | Pending
Post-Audit Activities & Closure
PA-01 | Submit final audit report to Executive Committee and Audit Committee | Chief Auditor, Board Secretary | 2023-12-03 | Pending
PA-02 | Conduct post-audit review meeting to assess process effectiveness and lessons learned | Audit Team, HR Representative | 2023-12-06 | Pending
Follow-up Schedule & Tracking System Setup
FS-01 | Establish follow-up timeline and tracking mechanism for corrective actions | Audit Team, Compliance Officer | 2023-12-08 | Pending
Audit Preparation Complete - Status: In Progress