## Worksheet
Audit Preparation Planner - Small Business
Task | Responsible Party | Due Date | Status | Supporting Documents/Notes
Review Financial Statements (Q1) | Accountant | 2024-04-15 | Pending | Balance sheet, P&L, cash flow
Collect and organize invoices (Jan - Mar) | Finance Team | 2024-04-10 | In Progress | PDFs and original copies in shared drive
Verify Bank Reconciliation Statements | Cashier / Accountant | 2024-04-18 | Pending | Monthly statements, adjustment entries
Confirm employee payroll records and tax filings | HR & Payroll Coordinator | 2024-04-12 | Pending | Payroll register, W-2s, 1099s
Update Fixed Asset Register | Finance Manager | 2024-04-16 | Pending | Add new purchases, disposal records
Review contracts and lease agreements | Legal / Office Manager | 2024-04-14 | Pending | All active contracts in file cabinet + digital copy
Conduct Internal Audit Walkthrough | Internal Auditor | 2024-04-19 | Pending | Checklists, risk assessments, observations
Clean Up and Finalize Audit File Package | Accountant & Project Lead | 2024-04-25 | Pending | Organized by category, labeled, indexed for review
This template is designed for small business audit preparation. Update status regularly and ensure all documents are retained for at least seven years.