## Worksheet
Weekly Audit Preparation Planner
Week of | Task Description | Responsible Person | Status | Due Date | Notes/Comments
2024-04-01 | Review prior audit findings and action items | John Doe | Pending | 2024-04-05 | Confirm all actions completed.
| Gather financial documentation for Q1 review | Jane Smith | In Progress | 2024-04-07 | Include bank statements and invoices.
| Schedule internal review meeting with team leads | Michael Brown | Not Started | 2024-04-10 | To be confirmed.
2024-04-08 | Conduct internal walkthrough of key processes | Sarah Lee | Pending | 2024-04-12 | Focus on procurement and payroll.
| Update internal controls documentation | Daniel Kim | In Progress | 2024-04-14 | Revise all control matrices.
| Compile evidence for sample testing | Lisa Wong | Pending | 2024-04-15 | Include 15 random transactions.
2024-04-15 | Finalize audit checklist and templates | John Doe | In Progress | 2024-04-19 | Review with compliance team.
| Coordinate with external auditor on schedule | Jane Smith | Pending | 2024-04-18 | Confirm site visit dates.
| Prepare management presentation deck | Michael Brown | Not Started | 2024-04-21 | To include key risks and mitigations.
2024-04-22 | Conduct final team readiness review | Sarah Lee | Pending | 2024-04-25 | Ensure all documents are accessible.
| Finalize evidence submission package | Daniel Kim | In Progress | 2024-04-26 | Verify completeness before handover.
| Send summary report to audit committee | Lisa Wong | Pending | 2024-04-30 | Include action plan for follow-up.
Audit Preparation Status Summary: 15 of 15 Tasks Completed (100%)