## Worksheet
Audit Preparation - Project Plan
Advanced Template ¦ Prepared for Comprehensive Audit Readiness
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Prioritization Level
TASK-001 | Review financial documentation from Q1 2023 | Audit Team Lead | 2024-04-05 | 2024-04-15 | In Progress | High
TASK-002 | Validate internal controls for procurement process | Compliance Officer | 2024-04-06 | 2024-04-18 | Pending | High
TASK-003 | Conduct employee interviews on policy adherence | HR & Audit Liaison | 2024-04-10 | 2024-04-25 | Pending | Medium
TASK-004 | Prepare audit checklist and working papers | Audit Coordinator | 2024-04-12 | 2024-04-30 | In Progress | High
TASK-005 | Review IT system access logs for anomalies | IT Security Analyst | 2024-04-14 | 2024-05-10 | Pending | High
TASK-006 | Compile summary report for executive review | Senior Audit Manager | 2024-05-15 | 2024-05-31 | Pending | Medium
TASK-007 | Conduct internal audit readiness workshop | Training Director | 2024-05-18 | 2024-05-19 | Pending | Low