## Worksheet
Audit Preparation - Project Plan (Analysis View)
Task ID | Activity | Owner | Start Date | End Date | Status | % Complete | Risk Level(Impact/Probability)
TASK-001 | Review Audit Scope & Objectives | John Smith | 2025-04-01 | 2025-04-03 | On Hold
TASK-002 | Gather Financial Records (Q1) | Sarah Johnson | 2025-04-04 | 2025-04-15 | In Progress
TASK-003 | Map Internal Controls & Processes | David Lee | 2025-04-30In Progress
TASK-004 | Conduct Preliminary Risk Assessment | Lisa Wang | 2025-05-01 | 2025-05-14 | Not Started | Not Started | Low (3/4)
TASK-005 | Develop Audit Testing Plan | Michael Brown | 2025-05-15 | 2025-06-19 | Not Started | Not Started | Low (3/4)
TASK-006 | Coordinate with External Auditors | Sophia Garcia | 2025-04-28 | 2025-05-17 | In Progress | 65%
TASK-007 | Training & Onboarding Team | Jamal Patel | 2025-04-18 | 2025-04-30 | Not Started | Not Started | Low (3/4)
TASK-008 | Prepare Documentation Repository | Emily Chen | 2025-04-15 | 2025-04-30 | On Hold | 35%
TASK-009 | Conduct Internal Walkthroughs | Nathan Kim | 2025-06-20 | 2025-07-18 | Not Started | Not Started | Medium (4/3)
TASK-010 | Audit Execution & Fieldwork | Team Lead - Audit Department | 2025-07-19 | 2025-08-31 | Not Started | Not Started | High (4/4)