## Worksheet
Annual Project Plan - Audit Preparation
Phase | Task Description | Responsible Team/Person | Start Date | End Date | Status
Phase 1 Planning & Preparation | Define audit scope and objectives for the year | Audit Team Lead | 2023-01-05 | 2023-01-15 | Pending
| Identify key departments and systems to audit | Risk Management Team | 2023-01-16 | 2023-01-31 | In Progress
| Develop audit checklist and risk assessment matrix | Audit Team + Compliance Officers | 2023-02-01 | 2023-02-15 | In Progress
| Finalize annual audit schedule with stakeholders | Audit Team Lead | 2023-02-16 | 2023-02-28 | Pending
Phase 2 | Conduct initial interviews with department heads | Audit Team Members | 2023-03-01 | 2023-03-15 | Pending
| Review documentation and control procedures | Audit Team + IT Security | 2023-03-16 | 2023-04-15 | Pending
| Perform risk-based testing on critical controls | Audit Team + External Consultants (if needed) | 2023-04-16 | 2023-05-15 | Pending
| Document findings and issues with evidence | Audit Team Members | 2023-05-16 | 2023-05-31 | Pending
| Conduct draft audit findings review with management | Audit Team Lead + Department Heads | 2023-06-01 | 2023-06-15 | Pending
Phase 3 Reporting & Follow-up | Prepare final audit report with recommendations | Audit Team Lead + Compliance Officer | 2023-06-16 | 2023-07-15 | Pending
| Present findings to Audit Committee | Audit Team Lead + CFO & CEO | 2023-07-16 | 2023-07-31 | Pending
| Implement corrective action plans with responsible parties | Department Managers + Compliance Team | 2023-08-01 | 2023-10-31 | Pending
| Conduct follow-up review of corrective actions (Q4) | Audit Team + Internal Control Office | 2023-11-01 | 2023-12-31 | Pending
Total Duration: |  |  |  |  | Jan 5 - Dec 31, 2023