## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status
TASK001 | Define Audit Scope and Objectives | Audit Team Lead | 2024-04-01 | 2024-04-05 | Not Started
TASK002 | Collect and Review Documentation | Documentation Coordinator | 2024-04-06 | 2024-04-15 | In Progress
TASK003 | Conduct Initial Risk Assessment | Risk Analyst | 2024-04-16 | 2024-04-20 | Not Started
TASK004 | Schedule Audit Interviews and Meetings | Audit Coordinator | 2024-04-18 | 2024-04-25 | In Progress
TASK005 | Perform Fieldwork and Testing | Audit Team Members | 2024-04-26 | 2024-05-10 | Not Started
TASK006 | Document Findings and Issues | Audit Lead | 2024-05-11 | 2024-05-17 | Not Started
TASK007 | Prepare Draft Audit Report | Report Writer | 2024-05-18 | 2024-05-25 | Not Started
TASK008 | Review and Approve Final Report | Audit Committee | 2024-05-26 | 2024-06-01 | Not Started
TASK009 | Distribute Audit Findings to Management | Compliance Officer | 2024-06-02 | 2024-06-05 | Not Started
TASK010 | Follow-up on Action Items and Remediation Plans | Audit Follow-up Officer | 2024-06-06 | 2024-06-30 | Not Started