## Worksheet
Phase | Task Description | Responsible Team | Start Date | End Date | Status | Milestones/Notes(Key deliverables)(Attach documents where applicable)
Phase 1 | Define Audit Scope and Objectives | Audit Team, Finance Department | 2024-04-01 | 2024-04-15 | In Progress | Finalize audit scope document and obtain management approval.Deliverable:Approved Audit Scope Document (v1.0)
Phase 2 | Gather Financial and Operational Records | Finance, IT, Operations | 2024-04-16 | 2024-05-15 | In Progress | Collect all relevant documents including ledgers, contracts, and system logs.Deliverable:Complete Document Repository (ZIP/Shared Drive)
Phase 3 | Perform Preliminary Risk Assessment | Risk Management Team, Internal Audit | 2024-05-16 | 2024-06-05 | Completed | Identify high-risk areas and prioritize audit focus.Deliverable:Risk Assessment Report (v1.1)
Phase 4 | Conduct On-Site Audit Procedures | Audit Team, Department Heads | 2024-06-06 | 2024-07-15 | Delayed (Pending Resource Allocation) | Field testing, sampling, and walkthroughs of key processes.Deliverable:Audit Working Papers & Findings Log
Phase 5 | Compile Audit Report and Recommendations | Audit Lead, Compliance Office | 2024-07-16 | 2024-08-05 | Completed | Finalize report with executive summary and action plans.Deliverable:Draft Audit Report (v3.2)
Phase 6 | Presentation to Executive Leadership | Audit Team, CFO, CEO Office | 2024-08-06 | 2024-08-15 | Completed | Present findings and receive feedback.Deliverable:Approved Final Audit Report & Action Tracker
Notes:This project plan is intended for internal business use and aligns with standard audit preparation practices. All timelines are subject to change based on resource availability and management review.