## Worksheet
Audit Preparation - Project Plan (Client View)
Phase | Task | Responsible Party | Start Date | End Date | Status | Deliverables
Phase 1: Planning & Scoping
Planning | Define audit objectives and scope | Client Project Lead | 2024-04-01 | 2024-04-05 | In Progress | Audit Scope Document (v1.0)
Planning | Identify key stakeholders and contacts | Client Project Lead, Audit Team Lead | 2024-04-06 | 2024-04-10 | Pending | List of Stakeholders (Approved)
Phase 2: Documentation Gathering
Documentation Collection | Gather financial statements and supporting records | Client Finance Team, Audit Support Staff | 2024-04-11 | 2024-04-30 | Pending | Complete financial documentation package
Documentation Collection | Collect operational and compliance records | Operations Manager, Compliance Officer | 2024-04-15 | 2024-05-10 | Pending | Compliance documentation bundle (v1.5)
Phase 3: Review & Testing
Review | Conduct preliminary review of financial data | Audit Team Lead, Senior Auditor | 2024-05-13 | 2024-05-27 | Pending | Preliminary findings report (draft)
Testing | Perform sample testing of transactions and controls | Audit Team, Internal Control Specialist | 2024-05-15 | 2024-06-15 | Pending | Test results documentation (v1.8)
Phase 4: Finalization & Reporting
Finalization | Compile audit findings and draft final report | Audit Team Lead, Senior Auditor | 2024-06-18 | 2024-07-15 | Pending | Draft Audit Report (v3.1)
Reporting | Present final findings to client management and board | Audit Team Lead, Client Executive Team | 2024-07-16 | 2024-07-19 | Pending | Final Audit Report & Presentation Deck (v3.5)
Total Duration: |  |  |  | 2024-04-01 to 2024-07-19 (13 weeks)
This project plan template is designed for client view presentation during audit preparation. All dates are subject to change based on client feedback and availability.