## Worksheet
Task | Responsible | Start Date | End Date | Status | Notes
Define Audit Scope | Audit Manager | 2024-01-05 | 2024-01-10 | In Progress | Review prior audit findings
Gather Documentation | Team Lead | 2024-01-11 | 2024-01-18 | Not Started | Compile all policy and procedure files
Interview Key Personnel | Auditor A | 2024-01-19 | 2024-01-25 | Not Started | Schedule with department heads
Risk Assessment Review | Risk Officer | 2024-01-26 | 2024-01-31 | Not Started | Evaluate current control effectiveness
Draft Audit Report | Lead Auditor | 2024-02-01 | 2024-02-07 | Not Started | Include recommendations and action items
Review & Approve Report | Audit Committee | 2024-02-08 | 2024-02-15 | Not Started | Final sign-off before distribution
Close Audit | Audit Manager | 2024-02-16 | 2024-02-17 | Not Started | Archive files and update audit log