## Worksheet
Audit Preparation - Project Plan
Dashboard View ¦ Template Type: Project Plan ¦ Purpose: Audit Preparation
Task ID | Task Description | Responsible Team | Start Date | Due Date | Status | Progress (%)
TASK001 | Define audit scope and objectives | Internal Audit Team | 2025-04-01 | 2025-04-05 | Completed
TASK002 | Collect financial records and documentation | Finance Department | 2025-04-06 | 2025-04-15 | Ongoing
TASK003 | Review compliance with internal policies | Compliance Team | 2025-04-16 | 2025-04-25 | Ongoing
TASK004 | Conduct field audit procedures | Audit Field Team | 2025-04-26 | 2025-05-10 | Delayed
TASK005 | Prepare draft audit report | Audit Reporting Team | 2025-05-11 | 2025-05-20 | Delayed
TASK006 | Finalize audit report and obtain approvals | Senior Audit Manager | 2025-05-21 | 2025-05-31 | Delayed
Project Summary
Total Tasks: | 6 | Completed: | 1 (16.7%)
Ongoing: | 2 (33.3%) | Delayed: | 3 (50.0%)
Avg. Progress: | 28.3%
This project plan is designed for audit preparation and will be updated weekly.