## Worksheet
AUDIT PREPARATION - PROJECT PLAN (DATA VERSION)
Phase | Task Description | Responsible Party | Start Date | End Date | Status | Milestones/Checkpoints | Notes/Comments
Phase 1: Planning | Define audit scope, objectives, and key areas of focus. | Lead Auditor | 2024-04-01 | 2024-04-05 | In Progress | Finalize scope document (Draft 1) | Include input from department heads.
| Identify key personnel and allocate team members. | Audit Team Coordinator | 2024-04-06 | 2024-04-10 | Pending | Team assignment finalized and approved. | Ensure cross-functional representation.
| Develop initial audit checklist and data collection tools. | Data Lead & Compliance Officer | 2024-04-11 | 2024-04-15 | Pending | Checklist draft completed and reviewed. | Use standardized templates for consistency.
Phase 2: Data Collection | Gather financial, operational, and compliance documents. | Field Auditors | 2024-04-16 | 2024-04-30 | Pending | Document repository updated weekly. | All data must be verified and timestamped.
| Conduct interviews with key staff and process owners. | Audit Team Leads | 2024-05-01 | 2024-05-10 | Pending | Interview logs and summaries completed. | Schedule in advance with HR coordination.
| Validate data integrity and completeness using automated tools. | Data Analysts | 2024-05-11 | 2024-05-17 | Pending | Data validation report generated. | Use checksum and range validation checks.
Phase 3: Analysis | Perform detailed review of policies, controls, and procedures. | Audit Team Leads | 2024-05-18 | 2024-05-31 | Pending | Control effectiveness matrix updated. | Benchmark against industry standards.
| Identify risks, gaps, and non-conformities in processes. | Risk Analyst & Compliance Officer | 2024-06-01 | 2024-06-15 | Pending | Risk register updated with severity ratings. | Use 3-tier risk classification: Low, Medium, High.
Phase 4: Reporting | Prepare draft audit report with findings and recommendations. | Lead Auditor | 2024-06-16 | 2024-06-25 | Pending | Draft report circulated for internal review. | Incorporate feedback from team leads.
| Present findings to management and key stakeholders. | Audit Team Lead | 2024-06-26 | 2024-06-30 | Pending | Stakeholder briefing session completed. | Gather action item commitments.
| Finalize and issue the official audit report. | Lead Auditor & Compliance Officer | 2024-07-01 | 2024-07-15 | Closed | Report approved and filed. | Distribute to board, executives, and audited departments.
Total Project Duration: 105 Days (April 1 – July 15, 2024)