## Worksheet
AUDIT PREPARATION - DETAILED PROJECT PLAN
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Priority | Budget (USD) | Progress (%) | Risk Level | Notes/Comments
TASK-001 | Define Audit Scope and Objectives | Audit Lead, Finance Team | 2023-10-02 | 2023-10-05 | Completed | High | $5,000 | 100% | Low | Signed off by management.
TASK-002 | Gather Financial Documents (Q1–Q3) | Accounting Department | 2023-10-06 | 2023-10-15 | In Progress | High | $8,500 | 75% | Medium | Pending final sign-off on 3rd quarter reports.
TASK-003 | Review Compliance with Internal Policies | Compliance Officer | 2023-10-16 | 2023-10-25 | In Progress | High | $4,000 | 55% | Medium | Audit checklist updated on 10/12.
TASK-004 | Conduct Interviews with Department Heads | Audit Team, HR Coordinator | 2023-10-26 | 2023-11-05 | Pending | Medium | $6,750 | 0% | Low | Schedule confirmation pending.
TASK-005 | Prepare Audit Workpapers and Checklists | Audit Analysts | 2023-11-06 | 2023-11-15 | Pending | Medium | $7,800 | 0% | Low | Draft available in shared drive.
TASK-006 | Perform Field Audit Testing (Sample Review) | Audit Team Lead | 2023-11-16 | 2023-11-30 | Pending | High | $9,500 | 0% | High | Requires approval of sample size.
TASK-007 | Compile Audit Findings and Recommendations | Audit Analysts, Lead Auditor | 2023-12-01 | 2023-12-15 | Pending | High | $6,400 | 0% | Medium | To be reviewed by internal committee.
TASK-008 | Submit Draft Audit Report to Management | Audit Lead | 2023-12-16 | 2023-12-18 | Pending | High | $3,500 | 0% | Low | Pending final review by compliance.
TOTAL PROJECT BUDGET | [6 empty] | $51,450 | — | —