## Worksheet
Audit Preparation - Project Plan (Employee View)
Task ID | Task Description | Assignee | Due Date | Status | Priority(High/Med/Low) | % Complete
AP-001 | Review financial records for Q3 2023 | Sarah Johnson | 2024-11-30 | In Progress | High(Critical) | 75%
AP-002 | Gather HR documentation for compliance audit | Michael Torres | 2024-11-30 | In Progress | High(Critical) | 60%
AP-003 | Update internal control policies documentation | Jessica Wu | 2024-12-15 | Pending Start | Medium | 0%
AP-004 | Conduct internal walkthrough with department leads | David Chen | 2024-12-10 | Pending Start | High(Critical) | 0%
AP-005 | Prepare audit response templates for feedback review | Linda Patel | 2024-12-18 | Pending Start | Medium | 0%
AP-006 | Finalize audit checklist and distribute to team | James Reed | 2024-12-25 | Pending Start | High(Critical) | 0%
AP-007 | Conduct mock audit session with IT and finance teams | Amina Diallo | 2024-12-16 | Pending Start | High(Critical) | 0%
AP-008 | Compile final audit package and submit to lead auditor | Robert Kim | 2025-01-15 | Pending Start | High(Critical) | 0%
© 2024 Audit Preparation Team ¦ Project Plan (Employee View) ¦ For Internal Use Only