## Worksheet
Audit Preparation - Project Plan (Extended)
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
Phase 1: Planning & Scoping
P1-001 | Define audit objectives and scope | Audit Manager | 2024-04-05 | 2024-04-15 | In Progress | $1,500
P1-002 | Identify key stakeholders and departments involved | Project Coordinator | 2024-04-16 | 2024-04-18 | Pending Approval | $500
Phase 2: Documentation Gathering
P2-001 | Collect financial records and transaction logs (Q1) | Finance Team | 2024-04-19 | 2024-05-31 | In Progress | $3,750
P2-002 | Obtain HR policies and compliance records for review | HR Department | 2024-04-19 | 2024-05-15 | Closed (Completed) | $850
Phase 3: Internal Review & Testing
P3-001 | Conduct internal control testing on procurement processes | Audit Team Lead | 2024-05-16 | 2024-06-15 | In Progress | $7,300
P3-002 | Perform data validation and reconciliation of key accounts | Internal Auditor - Data Analyst | 2024-06-16 | 2024-07-15 | Pending Start | $6,950
Phase 4: Reporting & Finalization
P4-001 | Compile audit findings and draft report | Lead Auditor | 2024-07-16 | 2024-08-15 | Pending Start | $9,800
P4-002 | Review and finalize audit report with management team | Management & Audit Committee | 2024-08-16 | 2024-08-31 | Pending Start | $5,500
Total Estimated Budget: | [5 empty] | $42,150
Notes:All dates are in YYYY-MM-DD format. Status values include: Pending Start, In Progress, Pending Approval, Closed (Completed).