## Worksheet
Audit Preparation - Financial View Project Plan
Phase | Task Description | Start Date | End Date | Responsible Team | Budget (USD) | Budget Utilized (USD) | Status
Phase 1: Planning & Scope Definition
1.1 | Define Audit Objectives and Scope | 2025-04-01 | 2025-04-07 | Audit Team Lead | 15,000.00 | 3,875.67 | In Progress
Phase 2: Documentation & Data Collection
2.1 | Gather Financial Statements (Q1-Q4) | 2025-04-08 | 2025-04-18 | Finance Department | 8,500.00 | 6,317.42 | In Progress
Phase 3: Internal Review & Verification
Phase 4: Final Reporting and Submission
Total Budget: |  |  |  |  | 32,000.00 | 12,876.94 | N/A