## Worksheet
Audit Preparation - Freelancer Project Plan
Phase | Task Description | Assigned To | Start Date | Due Date | Status
Phase 1: Planning & Scoping
1.1 | Define audit objectives and scope | Project Manager | 2024-04-05 | 2024-04-10 | Pending
1.2 | Identify key stakeholders and contacts | Lead Auditor | 2024-04-07 | 2024-04-15 | In Progress
Phase 2: Document & Process Review
2.1 | Collect and organize relevant documentation | Documentation Specialist | 2024-04-16 | 2024-04-30 | Pending
2.2 | Review internal policies and compliance records | Compliance Officer | 2024-04-18 | 2024-05-15 | In Progress
Phase 3: Fieldwork & Assessment
3.1 | Conduct site visit and interviews | Audit Team Lead | 2024-05-16 | 2024-05-31 | Pending
3.2 | Verify control effectiveness and data accuracy | Auditor 1, Auditor 2 | 2024-05-18 | 2024-06-15 | Pending
Phase 4: Report Preparation & Delivery
4.1 | Compile audit findings and recommendations | Lead Auditor | 2024-06-16 | 2024-06-30 | Pending
4.2 | Prepare final audit report and presentation materials | Report Writer, Designer | 2024-06-18 | 2024-07-15 | Pending
Phase 5: Audit Closure & Follow-Up
5.1 | Present findings to management team | Project Manager, Lead Auditor | 2024-07-16 | 2024-07-25 | Pending
5.2 | Capture feedback and close audit file | Project Manager | 2024-07-26 | 2024-07-31 | Pending
Prepared on: 2024-04-05 ¦ Template Version: Freelancer - Project Plan v1.1