## Worksheet
Audit Preparation - Project Plan (Manager View)
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete
#AP001 | Define audit scope and objectives | John Smith | 2024-04-01 | 2024-04-05 | Completed | 100%
#AP002 | Identify key control areas | Jane Doe | 2024-04-03 | 2024-04-15 | In Progress | 75%
#AP003 | Compile relevant documentation | Robert Lee | 2024-04-10 | 2024-04-25 | In Progress | 55%
#AP004 | Conduct preliminary risk assessment | Lisa Wong | 2024-04-12 | 2024-05-15 | In Progress | 38%
#AP005 | Review internal policies and procedures | Michael Brown | 2024-04-15 | 2024-05-31 | Not Started | 0%
#AP006 | Develop audit checklist and working papers | Sarah Johnson | 2024-05-15 | 2024-06-15 | Not Started | 0%
#AP007 | Schedule audit team meetings and walkthroughs | David Kim | 2024-05-25 | 2024-06-15 | Not Started | 0%
#AP008 | Finalize audit plan and obtain approval | Emily Davis | 2024-06-15 | 2024-06-30 | Not Started | 0%