## Worksheet
Audit Preparation - Monthly Project Plan
Month | Task/Activity | Responsible Party | Status (Pending/In Progress/Completed) | Due Date | Notes / Dependencies
January 2024
January | Review prior audit findings and action items | Audit Team Lead | Pending | 2024-01-15 | Verify closure of all previous items.
January | Identify key audit areas and risk assessment | Risk Manager & Audit Team | Pending | 2024-01-25 | Incorporate internal control assessments.
February 2024
February | Develop audit checklist and testing procedures | Audit Team Lead, Compliance Officer | Pending | 2024-02-10 | Align with regulatory standards.
February | Coordinate with department heads for document requests | Audit Coordinator | Pending | 2024-02-15 | Schedule intake meetings.
March 2024
March | Conduct on-site audit activities (Phase 1) | Audit Team | Pending | 2024-03-05 | Field testing, interviews, document review.
March | Review findings and draft preliminary report | Audit Team Lead | Pending | 2024-03-20 | Incorporate feedback from team leads.
April 2024
April | Present preliminary findings to management | Audit Team Lead, CFO | Pending | 2024-04-10 | Seek approval for final report.
April | Finalize audit report and obtain sign-off | Audit Team Lead, Audit Committee | Pending | 2024-04-30 | All actions assigned; document approved.
May 2024
May | Monitor implementation of corrective actions | Compliance Officer, Department Managers | Pending | 2024-05-15 | Determine timeline and progress tracking.
June 2024
June | Conduct follow-up review of corrective actions | Audit Team Lead, Compliance Officer | Pending | 2024-06-30 | Document effectiveness and closure.
Total Tasks Completed: |  |  |  | 0 / 11
Generated on¦ Audit Preparation Project Plan (Monthly)