## Worksheet
Audit Preparation - Project Plan
Template Type: Project Plan ¦ Style/Version: Multi Page ¦ Purpose: Audit Preparation
Phase | Task | Description | Responsible Team/Person | Start Date | End Date | Status
1. Planning & Scoping | Define Audit Scope | Identify key processes, systems, and controls to be audited. | Lead Auditor | 2024-01-05 | 2024-01-10 | Pending
Deliverables: Scope Document, Stakeholder List
| Engage Stakeholders | Meet with department heads to confirm scope and gather input. | Project Coordinator | 2024-01-11 | 2024-01-15 | In Progress
2. Risk Assessment | Identify High-Risk Areas | Analyze historical data, incidents, and control weaknesses. | Risk Analysts | 2024-01-16 | 2024-01-25 | Pending
Deliverables: Risk Matrix, Priority List
| Review & Finalize Risk Ratings | Validate risk levels with audit committee. | Audit Committee | 2024-01-26 | 2024-01-31 | Pending
Phase | Task | Description | Responsible Team/Person | Start Date | End Date | Status
3. Fieldwork Preparation | Develop Audit Procedures | Create detailed checklists for each risk area. | Audit Team Lead | 2024-02-01 | 2024-02-15
Deliverables: Audit Checklists, Sampling Plan
| Train Audit Team | Conduct session on tools, standards, and reporting. | Training Coordinator | 2024-02-16
Deliverables: Training Materials, Attendance Log
4. Fieldwork Execution | Conduct On-Site Reviews | Perform interviews, document reviews, and testing. | Audit Team Members | 2024-02-18 | 2024-03-15
Deliverables: Working Papers, Evidence Logs
| Document Findings | Log all observations with supporting evidence. | Lead Auditor | 2024-03-16
Phase | Task | Description | Responsible Team/Person | Start Date | End Date th> | Status
5. Reporting | Prepare Draft Report | Compile findings, conclusions, and recommendations. | Audit Team Lead | 2024-03-18
Deliverables: Draft Audit Report, Summary Presentation
| Review with Management | Present findings and receive feedback. | Management Representative | 2024-03-25
6. Closure | Finalize Audit Report | Update based on feedback, obtain sign-off. | Lead Auditor | 2024-04-01
Deliverables: Final Audit Report, Action Plan Summary
| Close Audit File | Archive documentation and close project. | Audit Manager | 2024-04-05
Audit Preparation - Project Plan ¦ Page 1 of 3 ¦ Generated: 2024-11-30