## Worksheet
Audit Preparation - Project Plan
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
TP-001 | Define Audit Scope and Objectives | Lead Auditor | 2024-04-01 | 2024-04-15 | In Progress | 75%
TP-002 | Assemble Audit Team and Assign Roles | HR & Project Manager | 2024-04-16 | 2024-04-18 | Not Started | 5%
TP-003 | Gather Financial and Operational Documents | Finance Team | 2024-04-19 | 2024-05-15 | In Progress | 65%
TP-004 | Conduct Preliminary Risk Assessment | Risk Management Unit | 2024-05-16 | 2024-05-31 | Not Started | 0%
TP-005 | Schedule On-Site Audit Sessions | Project Coordinator | 2024-06-01 | 2024-06-15 | Not Started | 5%
TP-006 | Review Compliance with Internal Policies | Compliance Officer | 2024-06-16 | 2024-07-15 | Not Started | 0%
TP-007 | Prepare Final Audit Report Draft | Audit Lead & Reporting Team | 2024-07-16 | 2024-08-15 | Not Started | 5%
TP-008 | Distribute Draft Report for Review | Project Manager | 2024-08-16 | 2024-09-30 | Not Started | 5%
TP-009 | Circulate Final Audit Report to Stakeholders | Audit Committee & Executives | 2024-10-01 | 2024-10-31 | Not Started | 5%
Total Tasks: | [5 empty] | 9
Prepared by: [Prepared By Name] ¦ Date: 2024-03-25 ¦ Version: 1.0