## Worksheet
Audit Preparation - Project Plan
Task ID | Task Description | Responsible Team/Person | Start Date | End Date | Status | Notes/Comments
T001 | Define audit scope and objectives | Audit Lead Team | 2023-10-01 | 2023-10-05 | In Progress | N/A
T002 | Review relevant policies and procedures | Compliance Department | 2023-10-06 | 2023-10-15 | Pending | In progress on document collection.
T003 | Collect and organize financial records | Finance Team | 2023-10-16 | 2023-10-25 | Pending | N/A
T004 | Conduct internal process walkthroughs | Audit Team & Process Owners | 2023-10-26 | 2023-11-05 | In Progress | N/A
T005 | Identify and document risks and control gaps | Risk & Audit Team | 2023-11-06 | 2023-11-15 | Pending | N/A
T006 | Prepare draft audit report and recommendations | Audit Lead Team | 2023-11-16 | 2023-11-25 | Pending | N/A
T007 | Review and finalize audit report with management | Audit Team & Executive Management | 2023-11-26 | 2023-12-05 | Pending | N/A
T008 | Submit final audit report to Audit Committee | Audit Lead Team | 2023-12-06 | 2023-12-10 | Pending | N/A