## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
T001 | Define Audit Scope and Objectives | Audit Manager | 2023-10-01 | 2023-10-05 | In Progress | 75%
T002 | Collect Financial Records and Documents | Finance Team | 2023-10-06 | 2023-10-15 | To Do | 0%
T003 | Review Internal Controls and Policies | Risk & Compliance Officer | 2023-10-16 | 2023-10-25 | To Do | 0%
T004 | Conduct On-Site Audit Activities | Audit Team | 2023-10-26 | 2023-11-05 | To Do | 0%
T005 | Prepare Draft Audit Report | Audit Lead | 2023-11-06 | 2023-11-15 | To Do | 0%
T006 | Review and Finalize Audit Report | Audit Manager & Stakeholders | 2023-11-16 | 2023-11-25 | To Do | 0%
T007 | Present Findings to Management | Audit Team Lead | 2023-11-26 | 2023-11-30 | To Do | 0%