## Worksheet
Audit Preparation - Project Plan (Planning View)
Phase | Task | Responsible Party | Start Date | End Date | Status | % Complete
Phase 1: Planning & Initiation
Planning | Define audit scope and objectives | Project Manager | 2025-04-01 | 2025-04-05 | In Progress | 75%
Planning | Identify key stakeholders | Team Lead | 2025-04-03 | 2025-04-07 | In Progress | 60%
Phase 2: Documentation & Review
Documentation | Compile financial records and supporting documents | Finance Team | 2025-04-06 | 2025-04-15 | To Do | 0%
Documentation | Gather policy and compliance documents | Compliance Officer | 2025-04-08 | 2025-04-18 | To Do | 0%
Phase 3: Internal Audit & Testing
Internal Review | Perform preliminary review of controls and processes | Audit Team | 2025-04-16 | 2025-04-25 | To Do | 0%
Milestone: Preliminary Audit Findings Report Complete - Due 2025-04-30
Phase 4: Finalization & Submission
Finalization | Address audit findings and update documentation | Department Heads | 2025-05-01 | 2025-05-10 | To Do | 0%
Finalization | Prepare final audit package and submit to external auditor | Project Manager | 2025-05-11 | 2025-05-15 | To Do | 0%
Final Milestone: Audit Submission Completed - Due 2025-05-15