## Worksheet
Audit Preparation - Project Plan
Printable Template ¦ Prepared for Audit Readiness
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status
T001 | Define audit scope and objectives | Audit Lead | 2024-04-01 | 2024-04-05 | Pending
T002 | Gather financial documentation for last 3 years | Finance Team | 2024-04-06 | 2024-04-15 | In Progress
T003 | Review internal controls and process documentation (Department 1)
T004 | Review internal controls and process documentation (Department 2)
T005 | Conduct preliminary risk assessment
T006 | Develop audit checklist and working papers template | Audit Team Lead | 2024-04-18 | 2024-04-25 | Pending
T007 | Schedule audit team training session (internal) | Internal Audit Team |  |  | 2024-04-16 | In Progress
T015 | Finalize project plan and assign resources for audit fieldwork phase
Prepared on:¦ Version: 1.0 ¦ Printed for Internal Audit Use Only