## Worksheet
Audit Preparation - Project Plan
Phase | Task Description | Responsible Party | Start Date | End Date | Status | Milestones/Comments
Planning & Scoping | Define audit objectives, scope, and key risks. | Audit Manager | 2023-10-01 | 2023-10-05 | In Progress | Approval received from Compliance Team.
Data Collection | Gather financial records, system logs, and policy documents. | Internal Audit Team | 2023-10-06 | 2023-10-15 | Pending | Data request forms submitted to departments.
Internal Review | Review collected data for completeness and accuracy. | Lead Auditor | 2023-10-16 | 2023-10-20 | Pending | QA checklist completed.
Risk Assessment | Evaluate identified risks and prioritize audit areas. | Risk Management Team | 2023-10-21 | 2023-10-25 | Pending | High-risk areas flagged for deep dive.
Audit Fieldwork | Conduct on-site or remote testing of controls and processes. | Audit Team | 2023-10-26 | 2023-11-05 | Pending | Scheduled interviews with department heads.
Reporting & Findings | Compile audit results, draft report, and prepare recommendations. | Lead Auditor | 2023-11-06 | 2023-11-10 | Pending | Draft review by Legal and Compliance.
Management Response | Submit findings to management for response and action plans. | Audit Manager | 2023-11-11 | 2023-11-18 | Pending | Due date for responses set.
Closing Meeting & Final Report | Hold closing meeting, finalize report, and obtain sign-off. | Senior Audit Committee | 2023-11-19 | 2023-11-25 | Pending | Final approval pending from CFO.
This project plan is intended for internal audit use only. All dates are subject to change based on resource availability and business priorities.