## Worksheet
Phase | Task | Responsible Team/Person | Start Date | End Date | Status
Q1: January - March 2024
Planning | Define audit scope and objectives | Compliance Team | 01/05/2024 | 01/15/2024 | Pending
Planning | Identify key processes and controls for review | Risk & Compliance Lead | 01/16/2024 | 01/31/2024 | In Progress
Q2: April - June 2024
Execution | Conduct preliminary assessments and walkthroughs | Audit Team | 04/01/2024 | 04/30/2024 | Pending
Execution | Collect and review documentation and evidence | Data Analysts & Auditors | 05/01/2024 | 05/31/2024 | In Progress
Q3: July - September 2024
Execution | Perform detailed testing of controls | Audit Team | 07/01/2024 | 08/31/2024 | Pending
Q4: October - December 2024
Reporting | Compile findings and draft audit report | Audit Lead & Reporting Specialist | 10/01/2024 | 10/31/2024 | Pending
Reporting | Review and finalize audit report with stakeholders | Compliance & Management Team | 11/01/2024 | 11/30/2024 | Pending
Follow-up | Schedule remediation planning session with departments | Compliance Manager | 12/01/2024 | 12/15/2024 | Pending
Total Tasks: |  |  |  |  | 10
Note:This table is a template for audit preparation project planning. Update status and dates as execution progresses.