## Worksheet
Task | Responsible | Start Date | End Date | Status
Define audit objectives and scope | Audit Manager | 2023-10-01 | 2023-10-05 | In Progress
Collect relevant documentation | Team Member A | 2023-10-06 | 2023-10-15 | Pending
Review internal controls | Team Member B | 2023-10-16 | 2023-10-25 | Pending
Conduct on-site assessment | Audit Team Lead | 2023-10-26 | 2023-11-05 | Pending
Identify findings and risks | Audit Analyst | 2023-11-06 | 2023-11-10 | Pending
Prepare audit report draft | Audit Writer | 2023-11-11 | 2023-11-15 | Pending
Review and finalize report | Audit Manager | 2023-11-16 | 2023-11-20 | Pending
Total Duration | 70 days (from 2023-10-01 to 2023-11-20)