## Worksheet
Audit Preparation - Project Plan (Small Business)
Task | Responsible Party | Start Date | End Date | Status | Notes/Comments
Phase 1: Planning & Scoping
Define audit scope and objectives | Project Manager | 2025-04-01 | 2025-04-05 | In Progress | N/A
Identify key compliance requirements | Compliance Officer | 2025-04-06 | 2025-04-10 | Pending | Incorporate SOX, GDPR, and local regulations.
Phase 2: Documentation & Review
Collect financial records (Q1–Q4) | Accounting Team | 2025-04-11 | 2025-04-18 | Pending | Ensure all ledgers and bank statements are available.
Compile internal policies and procedures | HR & Legal Teams | 2025-04-19 | 2025-04-25 | Pending | Include HR, IT, and finance policies.
Phase 3: Internal Review & Gap Analysis
Conduct internal audit walkthrough | Audit Team Lead | 2025-04-26 | 2025-05-03 | Pending | Identify discrepancies and control gaps.
Phase 4: Finalization & Submission
Prepare final audit package for external review | Project Manager | 2025-05-04 | 2025-05-10 | Pending | Include all reports, evidence, and findings.
Final Deadline: Audit Submission Date
Prepared for Small Business Audit Preparation ¦ Last Updated: April 5, 2025