## Worksheet
Phase | Key Activities | Responsible Party | Status | Target Start Date | Target End Date
Pre-Audit Planning & Setup
1. Audit Scope Definition | Define audit objectives, boundaries, and key risk areas. | Lead Auditor | In Progress | 2024-01-05 | 2024-01-15
2. Resource Allocation | Assign team members and define roles. | Project Manager | Pending | 2024-01-16 | 2024-01-20
Audit Execution Phase
3. Document Collection & Review | Gather and validate relevant documentation. | Documentation Specialist | Pending | 2024-01-21 | 2024-01-31
4. Fieldwork & Testing | Perform field visits, interviews, and control testing. | Audit Team Members | Pending | 2024-02-01 | 2024-02-15
Post-Audit Activities
5. Findings Compilation | Document audit findings and evidence. | Lead Auditor | Pending | 2024-02-16 | 2024-02-25
6. Management Review & Reporting | Present results, obtain feedback, and draft final report. | Audit Team & Management | Pending | 2024-02-26 | 2024-03-10
Finalization & Follow-Up
7. Audit Report Approval | Secure final sign-off from stakeholders. | Compliance Officer | Pending | 2024-03-11 | 2024-03-15
8. Corrective Action Tracking | Monitor implementation of recommended actions. | Risk & Compliance Team | Pending | 2024-03-16 | Ongoing
Prepared by:Audit Planning Department ¦Date:2024-01-04
Note: This summary is a high-level overview. Detailed plans and timelines may be adjusted based on real-time progress and stakeholder feedback.