## Worksheet
Audit Preparation - Project Plan (Team Use)
Task ID | Task Description | Owner | Due Date | Status | Progress (%) | Notes/Comments
T001 | Identify Audit Scope and Objectives | Jane Doe (Lead Auditor) | 2023-10-15 | In Progress | 65% | Confirmed with Finance team.
T002 | Gather Financial Records (Q1-Q3) | John Smith (Finance) | 2023-10-18 | Pending | 0% | Waiting for access to accounting system.
T003 | Review Internal Controls Documentation | Alice Brown (Compliance) | 2023-10-20 | To Do | 0% | Schedule meeting with department heads.
T004 | Prepare Audit Checklists and Schedules | Mike Wilson (Audit Team) | 2023-10-17 | In Progress | 80% | Draft reviewed by lead auditor.
T005 | Conduct Team Kickoff Meeting | Jane Doe (Lead Auditor) | 2023-10-14 | Completed | 100% | All team members confirmed attendance.
Project Summary: 5 Tasks ¦ 2 Completed ¦ 2 In Progress ¦ 1 Pending