## Worksheet
Task ID | Task Description | Responsible Party | Start Date | Planned End Date | Actual End Date | Status | % Complete
TASK-001 | Define Audit Scope and Objectives | Lead Auditor | 2024-05-15 | 2024-05-18 | - | In Progress | 75%
TASK-002 | Collect and Review Prior Audit Reports | Audit Team | 2024-05-16 | 2024-05-19 | - | In Progress | 60%
TASK-003 | Identify Key Risk Areas and Controls | Risk Analysts | 2024-05-17 | 2024-05-21 | - | Not Started
TASK-004 | Develop Audit Checklists and Procedures | Audit Lead | 2024-05-18 | 2024-05-23- | In Progress
TASK-005 | Coordinate with Department Heads for Data Access | Project Coordinator | 2024-05-19 | 2024-05-24- | In Progress
TASK-006 | Conduct Preliminary Risk Assessment Workshop | Lead Auditor | 2024-05-20 | 2024-05-21- | In Progress
TASK-007 | Finalize Audit Plan and Schedule Approval | Project Manager | 2024-05-22 | 2024-05-31- | Not Started
TASK-008 | Begin Fieldwork: Document Review and Sampling | Audit Team | 2024-06-01 | 2024-06-15 | -Not Started
TASK-009 | Conduct Interviews with Key Personnel | Audit Team | 2024-06-05 | 2024-06-18-Not Started
TASK-010 | Compile Audit Findings and Draft Report | Audit Lead | 2024-06-15 | 2024-06-30-Not Started
Overall Progress: | [5 empty] | 45% Complete