## Worksheet
Weekly Project Plan - Audit Preparation
Week | Date Range | Task/Activity | Responsible Party | Status | Progress (%) | Notes/Comments
Week 1 | 04/01/2024 - 04/07/2024 | Define audit scope and objectives | Audit Lead | In Progress | 65% | Initial alignment with department heads.
Week 2 | 04/08/2024 - 04/14/2024 | Identify key documentation and data sources | Documentation Coordinator | Pending | 0% | To be initiated after scope approval.
Week 3 | 04/15/2024 - 04/21/2024 | Review financial statements and internal controls | Audit Team Members | To Do | 0% | Requires access to accounting systems.
Week 4 | 04/22/2024 - 04/28/2024 | Conduct preliminary risk assessment | Risk Analyst | To Do | 0% | Based on previous audit findings.
Week 5 | 04/29/2024 - 05/05/2024 | Interview key personnel and process owners | Audit Lead & Team | To Do | 0% | Scheduling in progress.
Week 6 | 05/06/2024 - 05/12/2024 | Prepare draft audit findings and recommendations | Audit Team | To Do | 0% | After completing fieldwork.
Week 7 | 05/13/2024 - 05/19/2024 | Presentation of findings to management | Audit Lead | To Do | 0% | Final review before presentation.
Week 8 | 05/20/2024 - 05/26/2024 | Finalize audit report and obtain sign-off | Audit Manager | To Do | 0% | Includes stakeholder feedback.
Total Tasks: |  |  |  | 8