## Worksheet
Phase | Task Description | Responsible Team | Start Date | Due Date | Status
Planning & Initiation Phase
Phase 1 | Define audit scope and objectives with stakeholders | Audit Leadership Team |  |  | Pending
Documentation Collection & Verification Phase
Phase 2 | Collect financial records, contracts, and compliance documents | Audit Support Team |  |  | Pending
Phase 3 | Verify completeness and accuracy of documentation set | Compliance Officers & Internal Audit |  |  | Pending
Review & Testing Phase
Phase 4 | Perform internal testing of financial controls and processes | Risk Management Team |  |  | Pending
Phase 5 | Identify discrepancies and document findings with evidence | Audit Field Team |  |  | Pending
Reporting & Closure Phase
Phase 6 | Prepare audit report with recommendations and action plan | Audit Lead & Reporting Team |  |  | Pending
Phase 7 | Present findings to executive leadership and board of directors | Audit Director |  |  | Pending
Phase 8 | Obtain sign-off and close audit cycle with documented follow-up actions | All Stakeholders |  |  | Pending
Note:This template is designed for large business audit preparation. Customize dates, team members, and tasks based on specific organizational needs.
Version:1.0 ¦Last Updated:April 5, 2024