## Worksheet
Audit Preparation - Project Template
Section | Description | Status | Responsible Party | Due Date
Project Initiation | Define audit scope, objectives, and timeline. | In Progress | Project Manager | 2023-10-15
Team Assignment | Assign audit team members and roles. | To Do | HR Coordinator | 2023-10-18
Risk Assessment | Evaluate risks and prioritize audit areas. | Not Started | Lead Auditor | 2023-10-20
Document Collection | Gather all relevant financial and operational documents. | In Progress | Document Specialist | 2023-10-25
Record Verification | Validate accuracy and completeness of records. | To Do | Audit Team Lead | 2023-10-30
On-Site Review | Conduct physical verification and interviews. | To Do | Audit Field Team | 2023-11-05
Testing Procedures | Perform substantive and compliance testing. | To Do | Audit Analysts | 2023-11-08
Issue Identification | List findings, observations, and recommendations. | To Do | Lead Auditor | 2023-11-10
Draft Report Preparation | Create initial audit report with findings. | To Do | Report Writer | 2023-11-15
Internal Review | Peer review of audit findings and report. | To Do | Review Committee | 2023-11-18
Management Response | Obtain feedback and responses from management. | To Do | Compliance Officer | 2023-11-20
Final Report Submission | Submit final audit report to stakeholders. | To Do | Audit Manager | 2023-11-25
Follow-Up Plan Development | Create action plan for unresolved issues. | To Do | Project Coordinator | 2023-11-30
Audit Closeout Meeting | Hold final meeting to close the audit cycle. | To Do | Lead Auditor | 2023-12-01
Archive Documentation | Store all audit records in secure repository. | To Do | Records Manager | 2023-12-05
Section | Description | Key Metrics & Indicators | Target Value | Status
Project Timeline Adherence | Percentage of tasks completed on schedule. | On-time Completion Rate | 95% | In Progress
Document Completeness Score | Average percentage of required documents collected. | Document Coverage Index | 98% | To Do
Testing Accuracy Rate | Percentage of tests with no errors. | Error-Free Testing Rate | 99% | To Do
Findings Resolution Time | Average days to resolve identified issues. | Avg. Resolution Duration (days) | ≤ 30 | To Do
Stakeholder Satisfaction Score | Average rating from audit stakeholders. | Satisfaction Index (1–10) | ≥ 8.5 | To Do
Risk Exposure Reduction | Percent reduction in high-risk areas post-audit. | Risk Mitigation Rate | ≥ 75% | To Do
Documentation Retention Rate | Percentage of audit records archived correctly. | Archival Success Rate | 100% | To Do
Audit Report Clarity Score | Rater score for report readability and clarity. | Clarity Index (1–10) | ≥ 9.0 | To Do
Audit Team Productivity Index | Tasks completed per team member per week. | Tasks/Week per Member | 5.0+ | To Do
Interview Effectiveness Score | Average score from interviewee feedback. | Interview Satisfaction (1–5) | ≥ 4.2 | To Do
Follow-Up Action Completion Rate | Percentage of recommended actions completed. | Action Closure Ratio | ≥ 90% | To Do
Audit Cycle Duration | Total time from initiation to closure. | Days per Audit Cycle | ≤ 60 | To Do
Area of Review | Control Objective | Evidence Type | Status | Notes / Observations
Financial Reporting Accuracy | Ensure all financial statements are accurate and compliant with GAAP. | Bank reconciliations, journal entries, trial balance | In Progress | Pending review of Q3 adjustments.
Access Controls | Restrict system access based on roles and responsibilities. | User access logs, role matrix, approval records | To Do | Review pending for IT department.
Change Management Process | Document and approve all system changes before implementation. | Change request forms, approval signatures | To Do | Pending documentation from IT team.
Segregation of Duties (SoD) | Prevent conflicts by separating incompatible roles. | Role assignments, process flowcharts | To Do | Six potential conflicts identified—review required.
Asset Protection | Ensure physical and digital assets are safeguarded. | Inventory records, surveillance logs, backup reports | To Do
Contract Management | Maintain accurate records and renewal schedules for contracts. | Contract register, renewal alerts, approval trails | To Do
Regulatory Compliance (e.g., SOX, GDPR) | Maintain compliance with applicable laws and regulations. | Compliance checklists, audit trails, legal reviews | To Do
Vendor Risk Management | Evaluate and monitor third-party vendors for risk. | Vendormonitoring reports, risk scores, due diligence records | To Do
Business Continuity Planning | Ensure recovery plans exist for critical systems. | BIA reports, DR test results, incident logs | To Do
Data Privacy Controls | Protect sensitive and personal information. | Data encryption logs, access reviews, consent records | To Do