## Worksheet
Audit Preparation - Project Template
Template Type:Project Template
Style/Version:Printable
Item ID | Description | Status | Responsible Party | Dates (Start - End) | Documentation Reference
IT-001 | Review of access control policies | Pending | Security Team | 2024-04-01 - 2024-04-15 | Policy Doc v3.1, Section 5.2
IT-002 | User access reviews for finance department | In Progress | HR & IT Coordinators | 2024-04-10 - 2024-04-30 | Access Review Form v2.0, April 2024
IT-003 | Backup system validation and testing | Completed | IT Operations Team | 2024-03-25 - 2024-04-05 | Test Report #BK-118, Executed 04/05/24
IT-004 | Evaluate change management process compliance | Pending | Change Advisory Board (CAB) | 2024-05-01 - 2024-05-15 | CAB Minutes, April 30 & May 7
IT-005 | Documentation of firewall rule sets | In Progress | Network Security Team | 2024-04-18 - 2024-05-10 | Firewall Config Backup, April 16, 2024
IT-006 | Review of third-party vendor access logs | Pending | Risk & Compliance Team | 2024-05-15 - 2024-05-31 | Vendor Access Log v3.7, April 30 Report
IT-007 | System patching status audit (Critical systems) | Completed | Server Admin Team | 2024-03-15 - 2024-03-31 | Patch Report #PS-99, March 31, 2024
IT-008 | Review of incident response plan effectiveness | In Progress | Incident Response Team | 2024-04-25 - 2024-05-15 | IRO Manual v4.3, Updated April 18, 2024
IT-009 | Asset inventory verification (Physical & Virtual) | Pending | Asset Management Team | 2024-05-15 - 2024-06-15 | Inventory List v7.1, May 3, 2024 Update
IT-010 | Final audit checklist review and sign-off | Pending | Audit Lead, Internal Control Team | 2024-06-15 - 2024-06-30 | Audit Checklist v9.0, Draft Review (May 31)
Prepared for: Internal Audit Department ¦ Prepared on: May 28, 2024 ¦ Version: 1.0
Note: This document is intended for audit preparation and printable use. All data subject to validation.