## Worksheet
Audit Preparation - Project Timeline
Advanced Template ¦ Status Tracking & Milestone Management
Phase / Task | Start Date | End Date | Status | Responsible Team | Milestones & Deliverables(Key checkpoints)
Pre-Audit Planning & Setup
Define Audit Scope & Objectives | 2024-01-05 | 2024-01-15 | In Progress | Audit Leadership | Finalize scope document, stakeholder sign-off
Assemble Audit Team & Assign Roles | 2024-01-16 | 2024-01-25 | Pending | HQ HR & Audit Lead | Team roster, role definitions, training schedule
Document Collection & Review Phase
Gather Financial Statements (Q4 2023) | 2024-01-18 | 2024-01-31 | Pending | Finance Department | Monthly reports, balance sheet, P&L statements
Review Internal Controls Framework | 2024-02-01 | 2024-02-15 | Pending | Internal Audit & Compliance Team | Control matrix, risk assessments, SOX documentation
Fieldwork & Testing Phase
Perform Substantive Testing (Sample Selection) | 2024-02-16 | 2024-03-15 | Pending | Audit Team - Fieldwork Unit | Sample transaction testing, reconciliations, confirmations
Interview Key Personnel & Process Owners | 2024-03-16 | 2024-03-31 | Pending | Audit Team - Fieldwork Unit | Process walkthroughs, control observations, gap identification
Reporting & Finalization Phase
Compile Audit Findings & Draft Report | 2024-04-01 | 2024-04-15 | Pending | Audit Lead & Reporting Unit | Summary of issues, risk ratings, recommendations, draft report
Review & Finalize Report with Management | 2024-04-16 | 2024-04-30 | Pending | Audit Committee & Executives | Feedback loop, management response, approval process
Post-Audit Follow-Up & Closure
Develop Action Plan & Assign Ownership | 2024-05-01 | 2024-05-15 | Pending | Risk & Compliance Office | Corrective action plans, timelines, responsible parties
Monitor Implementation & Conduct Follow-Up Review | 2024-05-16 | 2024-06-30 | Pending | Audit Team & Internal Control Unit | Progress tracking, evidence collection, closure validation
Total Duration | January 5, 2024 – June 30, 2024 (6 Months) |  |  |  | Final Audit Report Submission & Closure
Generated on¦ Audit Version 2.1