## Worksheet
Audit Preparation - Project Timeline (Analysis View)
Purpose: Audit Preparation ¦ Template Type: Project Timeline ¦ Style/Version: Analysis View
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Personnel | Milestones Achieved(Y/N)(%)
Planning & Scoping | Define audit objectives, scope, and key risk areas. | 2024-01-01 | 2024-01-15 | Completed | Audit Lead, Risk Team | Y / 100%(N/A)(N/A)(N/A) (N/A)
Data Collection | Gather financial statements, internal controls documentation, and compliance records. | 2024-01-16 | 2024-01-31 | Completed | Data Team, Compliance Officers | Y / 95%(N/A)(N/A)(N/A) (N/A)
Fieldwork & Testing | Conduct on-site reviews, perform testing of controls and transactions. | 2024-02-01 | 2024-03-15 | Ongoing | Audit Team, IT Security | N / 65%(N/A)(N/A)(N/A) (N/A)
Issue Identification | Document findings, root causes, and risk ratings. | 2024-03-16 | 2024-03-31 | Delayed | Audit Team, Risk Analysts | N / 45%(N/A)(N/A)(N/A) (N/A)
Reporting & Review | Prepare draft audit report, conduct internal review with compliance team. | 2024-04-01 | 2024-04-15 | Delayed | Audit Lead, Legal Counsel | N / 35%(N/A)(N/A)(N/A) (N/A)
Management Response | Collect responses and action plans from auditees. | 2024-04-16 | 2024-05-15 | Delayed | Department Heads, Audit Coordinator | N / 30%(N/A)(N/A)(N/A) (N/A)
Final Report & Approval | Publish final audit report and obtain approval from Audit Committee. | 2024-05-16 | 2024-06-30 | Delayed | Audit Committee, Senior Management | N / 15%(N/A)(N/A)(N/A) (N/A)