## Worksheet
Task | Responsible | Start Date | End Date | Status | Notes
Define Audit Scope | Audit Manager | 2023-10-01 | 2023-10-05 | Not Started
Gather Documentation | Audit Team | 2023-10-06 | 2023-10-15 | Not Started
Conduct Preliminary Review | Audit Lead | 2023-10-16 | 2023-10-20 | Not Started
Perform Fieldwork | Audit Team | 2023-10-21 | 2023-11-03 | Not Started
Draft Audit Findings | Audit Lead | 2023-11-04 | 2023-11-08 | Not Started
Review with Management | Audit Manager | 2023-11-09 | 2023-11-15 | Not Started
Finalize Audit Report | Audit Team | 2023-11-16 | 2023-11-20 | Not Started
Submit Audit Report | Audit Manager | 2023-11-21 | 2023-11-25 | Not Started