## Worksheet
Audit Preparation - Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Planning & Initiation | Define audit scope and objectives | 2024-01-05 | 2024-01-10 | Completed | Audit Lead Team
Documentation Collection | Gather financial records and compliance documents | 2024-01-11 | 2024-01-25 | In Progress | Finance & Compliance Team
Data Review & Validation | Verify accuracy and completeness of collected data | 2024-01-26 | 2024-02-05 | Pending | Data Integrity Unit
Risk Assessment | Identify key audit risks and materiality thresholds | 2024-02-06 | 2024-02-15 | Pending | Risk Management Team
Fieldwork & Testing | Conduct on-site reviews and sample testing | 2024-02-16 | 2024-03-15 | Pending | Audit Field Team
Findings & Reporting | Document audit findings and draft report | 2024-03-16 | 2024-03-31 | Pending | Audit Reporting Unit
Management Review & Approval | Submit draft report for management feedback and sign-off | 2024-04-01 | 2024-04-15 | Pending | Executive Management
Audit Closeout & Follow-up | Finalize audit report and schedule follow-up actions | 2024-04-16 | 2024-05-31 | Pending | Audit Coordinator