## Worksheet
Task | Responsible Party | Start Date | End Date | Status | Notes
Initial Audit Planning Meeting | Project Manager, Client Liaison | 2024-01-05 | 2024-01-10 | In Progress | Agenda prepared and shared with stakeholders.
Data Collection & Documentation Review | Internal Audit Team, Department Heads | 2024-01-11 | 2024-01-31 | Pending | Requires submission of all financial and operational records.
Risk Assessment & Materiality Determination | Audit Lead, Compliance Officer | 2024-02-01 | 2024-02-15 | Pending | Baseline risk matrix to be completed.
Audit Fieldwork Execution | Audit Team, Process Owners | 2024-02-16 | 2024-03-15 | Pending | On-site and remote verification of controls.
Audit Findings Compilation & Draft Report | Audit Lead, Reporting Analyst | 2024-03-16 | 2024-03-25 | Pending | Draft report to be reviewed by client.
Client Review & Feedback Session | Client Management, Audit Team | 2024-03-26 | 2024-04-05 | Pending | Meeting scheduled to discuss findings and recommendations.
Final Audit Report Submission | Audit Lead, Client Liaison | 2024-04-06 | 2024-04-10 | Pending | Final version approved and delivered to client.
Audit Closure & Lessons Learned Meeting | Project Manager, All Stakeholders | 2024-04-11 | 2024-04-15 | Pending | Closure documentation and feedback collected.