## Worksheet
Date | Task / Activity | Responsible Person(s) | Status
2023-10-01 | Define audit scope and objectives | Lead Auditor, Project Manager | In Progress
2023-10-02 | Identify key compliance areas and documentation requirements | Compliance Officer, IT Security Lead | In Progress
2023-10-03 | Compile and organize financial records and transaction logs | Finance Team, Data Analysts | In Progress
2023-10-04 | Review internal controls and process documentation | Internal Audit Team, Department Heads | In Progress
2023-10-05 | Conduct preliminary risk assessment and gap analysis | Risk Manager, Lead Auditor | In Progress
2023-10-06 | Update audit plan and schedule with stakeholder feedback | Project Manager, Audit Committee | In Progress
2023-10-07 | Finalize audit checklist and tools preparation | Lead Auditor, IT Support | In Progress
2023-10-08 | Conduct team training session on audit procedures | Lead Auditor, Training Coordinator | In Progress
2023-10-09 | Begin fieldwork - initial document review and interviews | Audit Team, Department Representatives | In Progress
2023-10-10 | Perform detailed testing of key financial and operational processes | Audit Team, Finance & Operations Leads | In Progress
2023-10-11 | Review findings and draft preliminary audit report sections | Lead Auditor, Report Writer | In Progress
2023-10-12 | Hold internal review meeting for audit findings and conclusions | Audit Committee, Lead Auditor, Department Heads | In Progress
2023-10-13 | Prepare final audit report with recommendations | Lead Auditor, Report Team | In Progress
2023-10-14 | Share draft report with management for feedback | Project Manager, Audit Committee | In Progress
2023-10-15 | Finalize audit report based on stakeholder input | Lead Auditor, Project Manager | In Progress
2023-10-16 | Conduct final audit closure meeting with leadership | Audit Committee, Senior Executives | In Progress
2023-10-17 | Archive all audit documentation and records | Records Manager, Compliance Officer | In Progress
2023-10-18 | Document lessons learned and process improvement suggestions | Project Manager, Audit Team | In Progress
2023-10-19 | Close audit project and update project timeline records | Project Manager, Admin Team | In Progress