## Worksheet
Audit Preparation - Project Timeline Dashboard
Audit Period: Q3 2024 ¦ Prepared on: October 5, 2024
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Progress (%)
TASK-001 | Document Collection and Categorization | Finance Team | 2024-09-01 | 2024-09-15 | Completed
TASK-002 | Internal Controls Review | Risk & Compliance | 2024-09-16 | 2024-10-03 | In Progress
TASK-003 | Process Mapping and Documentation | Operations | 2024-09-20 | 2024-10-15 | In Progress
TASK-004 | System Access Verification | IT Department | 2024-10-01 | 2024-10-15 | In Progress
TASK-005 | External Auditor Coordination | Audit Manager | 2024-10-16 | 2024-11-30 | Delayed
TASK-006 | Final Audit Report Preparation | Lead Auditor | 2024-11-15 | 2024-12-31 | Delayed