## Worksheet
Audit Preparation - Project Timeline
Phase/Task | Description | Responsible Team/Person | Start Date | End Date | Status | Milestones & Deliverables(Key Outputs)
1. Planning & Scoping | Define audit objectives, scope, and key areas of focus. | Audit Manager | 2024-01-05 | 2024-01-15 | In Progress | Finalized audit scope document, stakeholder sign-off.Initial risk assessment report.
1.1. Stakeholder Engagement | Meet with department heads to understand processes and concerns. | Audit Team Lead | 2024-01-05 | 2024-01-10 | Completed | Meeting minutes, updated risk matrix.Signed scope confirmation form.
1.2. Risk Assessment | Identify and prioritize audit risks based on data and prior findings. | Risk Analyst | 2024-01-11 | 2024-01-15 | In Progress | Risk register v. 1.0, audit risk scoring matrix.Review by Audit Committee.
2. Fieldwork & Data Collection | Conduct on-site reviews, interviews, and data extraction. | Audit Team (Field Staff) | 2024-01-16 | 2024-02-15 | Pending | Draft working papers, evidence logs.Data validation reports.
2.1. Document Review | Analyze financial records, policies, and compliance documentation. | Compliance Officer | 2024-01-16 | 2024-01-31 | Pending | Evidence checklist completed.Digital archives verified.
2.2. Process Interviews | Conduct structured interviews with key operational staff. | Audit Investigators | 2024-02-01 | 2024-02-15 | Pending | Interview summaries, process flow diagrams.Critical control gap identification.
3. Analysis & Testing | Analyze findings, perform substantive testing, validate conclusions. | Data Analysts & Lead Auditor | 2024-02-16 | 2024-03-15 | Pending | Test results, exception reports.Root cause analysis summaries.
3.1. Substantive Testing | Validate transactions and balances using statistical sampling. | Fraud Detection Team | 2024-02-16 | 2024-03-05 | Pending | Testing sample results.Detection rates, error frequency reports.
3.2. Control Evaluation | Assess the design and operating effectiveness of internal controls. | Internal Controls Specialist | 2024-03-06 | 2024-03-15 | Pending | Control evaluation matrix.Control deficiency summaries.
4. Reporting & Communication | Prepare final report, present findings, obtain feedback. | Audit Lead & Reporting Officer | 2024-03-16 | 2024-04-15 | Pending | Final audit report draft.Presentation slides for executive review.
4.1. Draft Report Preparation | Compile all findings into a structured audit report with recommendations. | Audit Reporting Team | 2024-03-16 | 2024-03-31 | Pending | Draft audit report v. 1.0.Executive summary ready for review.
4.2. Management Response & Review | Share findings with management and collect formal responses. | Audit Liaison | 2024-04-01 | 2024-04-10 | Pending | Management response letters.Closure tracking log updated.
4.3. Final Report & Presentation | Publish final report and present conclusions to leadership. | Audit Director | 2024-04-11 | 2024-04-15 | Pending | Final audit report issued.Presentation delivered to Board of Directors.Report archived in compliance portal.
5. Follow-Up & Closure | Monitor implementation of recommendations and verify closure. | Audit Follow-Up Team | 2024-04-16 | 2024-07-31 | Pending | Milestone tracking dashboard.Closure certificates for all action items.
5.1. Action Item Tracking | Monitor the implementation of corrective actions over time. | Follow-Up Coordinator | 2024-04-16 | 2024-07-31 | Pending | Monthly follow-up reports.Status update dashboards.
5.2. Final Closure & Archival | Confirm all actions are completed and archive all audit materials. | Compliance Archivist | 2024-07-30 | 2024-07-31 | Pending | Audit file closed.All documents securely stored.Final sign-off from Audit Committee.
Template Version: Detailed - Audit Preparation Project Timeline ¦ Last Updated: 2024-01-05