## Worksheet
Audit Preparation - Project Timeline
Phase | Task Description | Responsible Team/Person | Start Date | End Date | Status | Milestones & Deliverables(Key Items to Verify)
Phase 1: Planning & Scoping | Define audit objectives, scope, and key risks. | Audit Lead Team | 2024-04-01 | 2024-04-15 | Pending | - Approved audit plan - Stakeholder sign-off - Risk assessment report
Phase 2: Documentation Review | Gather and review financial, operational, and compliance records. | Documentation Specialists | 2024-04-16 | 2024-05-15 | In Progress | - Complete documentation inventory - Cross-reference with prior audit findings - Preliminary gap analysis report
Phase 3: Internal Controls Assessment | Evaluate design and operating effectiveness of internal controls. | Compliance & Control Team | 2024-05-16 | 2024-06-15 | In Progress | - Control matrix documentation - Testing samples completed - Identified control deficiencies report
Phase 4: Fieldwork & Data Collection | Conduct on-site verification, interviews, and sampling. | Audit Field Team | 2024-06-16 | 2024-07-15 | Pending | - Interview logs - Sample data collection - Evidence documentation folder updated
Phase 5: Findings & Reporting | Compile findings, draft audit report, and prepare recommendations. | Audit Report Team | 2024-07-16 | 2024-08-15 | Pending | - Draft audit report - Management response template ready - Executive summary prepared
Phase 6: Final Review & Approval | Review final draft, obtain sign-offs, and issue audit report. | Audit Committee & Senior Management | 2024-08-16 | 2024-08-31 | Pending | - Final audit report - Signed approval from audit committee - Distribution to stakeholders
Prepared for Audit Preparation ¦ Project Timeline (Extended Version)
Last Updated: April 5, 2024 ¦ Status as of current audit cycle