## Worksheet
Task | Start Date | End Date | Status | Budget Allocated ($) | Budget Spent ($)
Initial Audit Planning | 2024-01-05 | 2024-01-15 | In Progress | 15,000.00 | 8,756.34
Document Collection & Review | 2024-01-16 | 2024-01-31 | Not Started | 35,000.00 | -
Internal Control Assessment | 2024-02-01 | 2024-02-15 | Not Started | 45,000.00 | -
Fieldwork & Testing | 2024-02-16 | 2024-03-15 | Not Started | 75,000.00 | -
Audit Findings Report Draft | 2024-03-16 | 2024-03-31 | Not Started | 25,000.00 | -
Management Response & Corrective Actions | 2024-04-01 | 2024-04-15 | Not Started | 18,000.00 | -
Final Audit Report & Approval | 2024-04-16 | 2024-04-30 | Not Started | 15,000.00 | -
Total Project Budget |  |  |  |  | 228,000.00 | 8,756.34