## Worksheet
Audit Preparation - Project Timeline (Freelancer Style)
Phase | Task | Start Date | End Date | Responsible Team/Person | Status
Planning & Scoping | Define audit objectives and scope | 2024-03-01 | 2024-03-05 | Audit Lead, Project Manager | In Progress
| Identify key areas and stakeholders | 2024-03-06 | 2024-03-10 | Audit Team, HR Coordinator | Pending
Data Collection | Compile financial records (Q1–Q4 2023) | 2024-03-11 | 2024-03-18 | Fiscal Officer, Data Analyst | Pending
| Collect HR and compliance documentation | 2024-03-19 | 2024-03-25 | Compliance Officer, Admin Team | Pending
| Review internal policies and SOPs | 2024-03-26 | 2024-03-31 | Legal Advisor, Operations Manager | Pending
Analysis & Review | Conduct risk assessment and gap analysis | 2024-04-01 | 2024-04-10 | Audit Lead, Risk Analyst | Pending
| Validate findings with team leads | 2024-04-11 | 2024-04-15 | Audit Team, Department Heads | Pending
Reporting & Follow-up | Draft preliminary audit report | 2024-04-16 | 2024-04-23 | Audit Lead, Report Writer | Pending
| Presentation to management & feedback session | 2024-04-24 | 2024-04-30 | Audit Team, Executive Director | Pending
Finalization & Closure | Revise report based on feedback | 2024-05-01 | 2024-05-05 | Audit Lead, Project Manager | Pending
Total Duration: 90 Days ¦ Next Review Date: 2024-05-10
Template Version: Freelancer Style ¦ Created for Audit Preparation - Project Timeline