## Worksheet
Audit Preparation - Project Timeline
Large Business ¦ Audit Cycle: Q2 2024 ¦ Prepared on: April 5, 2024
Phase | Task Description | Start Date | End Date | Status | Responsible Team
Planning & Scoping | Define audit objectives, scope, and key risks. | April 10, 2024 | April 17, 2024 | Completed | Audit Leadership
Data Collection | Gather financial records, compliance documents, and system logs. | April 18, 2024 | May 5, 2024 | In Progress | Finance & IT Teams
Risk Assessment | Identify material risks and prioritize audit focus areas. | May 6, 2024 | May 12, 2024 | In Progress | Risk & Compliance
Fieldwork & Testing | Conduct detailed testing of internal controls and financial processes. | May 13, 2024 | June 7, 2024 | In Progress | Audit Field Team
Reporting & Drafting | Compile findings, prepare draft report, and review with stakeholders. | June 8, 2024 | June 18, 2024 | Completed | Audit Reporting Unit
Management Review & Approval | Present findings to senior management for feedback and approval. | June 19, 2024 | June 26, 2024 | Delayed | Executive Leadership
Final Audit Report & Closure | Issue final report, document action items, and close audit cycle. | June 27, 2024 | July 5, 2024 | Completed | Audit & Compliance Office