## Worksheet
Audit Preparation - Project Timeline (Manager View)
Phase / Task | Description | Owner | Start Date | End Date | Status
1. Planning & Scoping Phase
Define Audit Scope | Identify key departments and processes to audit. | John Smith (Audit Lead) | 2024-04-05 | 2024-04-15 | High
Develop Audit Plan | Create detailed audit schedule and resource allocation. | Emily Chen (Audit Coordinator) | 2024-04-16 | 2024-04-25 | Medium
2. Fieldwork Phase
Document Review | Collect and review key financial and operational documents. | Sarah Johnson (Lead Auditor) | 2024-04-26 | 2024-05-15 | Low
Interviews & Testing | Conduct stakeholder interviews and perform testing procedures. | David Kim (Audit Team) | 2024-05-16 | 2024-06-15 | Medium
3. Reporting & Follow-up Phase
Issue Draft Report | Compile preliminary findings and recommendations. | Rachel Lee (Report Writer) | 2024-06-16 | 2024-06-30 | Medium
Management Response | Receive and document responses from department heads. | All Audit Team Members | 2024-07-01 | 2024-07-15 | Low
Final Audit Report & Approval | Submit final report to executive committee for approval. | John Smith (Audit Lead) | 2024-07-16 | 2024-07-31 | High
4. Closure & Lessons Learned
Post-Audit Review Meeting | Conduct retrospective to evaluate audit effectiveness. | Jane Doe (Audit Manager) | 2024-08-01 | 2024-08-15 | Medium
Closedown & Archiving | Archive all documents and close the audit file. | Emily Chen (Audit Coordinator) | 2024-08-16 | 2024-08-31 | Low