## Worksheet
Audit Preparation - Project Timeline
Phase | Task Description | Owner | Start Date | End Date | Status
Planning | Define audit scope and objectives | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress
Data Collection | Gather financial and operational documents | John Smith | 2024-04-16 | 2024-05-10 | Pending
Review & Analysis | Analyze data for compliance and accuracy | Maria Lopez | 2024-05-11 | 2024-06-15 | Pending
Findings Documentation | Document audit findings and recommendations | Robert Kim | 2024-06-16 | 2024-07-05 | Pending
Report Finalization | Compile final audit report and obtain approval | Jane Doe | 2024-07-06 | 2024-07-15 | Pending
Stakeholder Review | Present findings to management and board | Daniel Brown | 2024-07-16 | 2024-07-31 | Pending
Total Duration: |  |  |  |  | 120 days